Instructions for Publishing a Notice of Intent to Request Release of Funds (NOI/RROF) for Nonprofits and For Profits

Publish in a local newspaper the NOIRROF once and begin the seven (7) day comment period after the publication date using the timetable below as reference.  The Notice cannot be published before the NOI/RROF is submitted to OHFA and OHFA has approved the Notice for publishing.

Step 1.  	Tiering instructions:  If tiering, be sure to include the tiering plan in the notice.

Step 2.  	The last day of the public comment period must be a day when the Contract Administrator is open for business.

Step 3. 	OHFA will consider the comments and make modifications, if appropriate, in response to the comments, before it completes its environmental certification and before the Contract Administrator can submit a RROF.  OHFA will consider public written comments received on or before the last day of comment period.

Step 4.  	After the seven (7) day comment period, OHFA prepares the R RROF (HUD Form 7015.15) (Attachment S).  The OHFA Certifying Officer will not sign the RROF nor send it to HUD before the end of the comment period.  OHFA will not submit the RROF to HUD until comments have been considered.

Step 5. 	OHFA A will fax the signed RROF and NOI/RROF (with affidavit if applicable) to HUD the day after the comment period to expedite the clearance process and will mail the originals to HUD.

Timetable for a Published NOI/RROF

Day 1	Contract Administrator publishes the NOI/RROF in the local newspaper once in accordance with 24 CFR 58.43.

Day 2	First day of seven (7) day comment period.

Day 8	Last day of seven (7) day comment period.

Note: OHFA will consider all remarks received up to and including the last day comment period and make modifications, if appropriate before processing the RROF and Certification (HUD Form 7015.15) (Attachment S).  The process may be delayed if there are comments that have to be addressed by the RE.

Day 9	The grantee faxes and mails the NOI/RROF and the original tear sheet from the newspaper (with date) to OHFA. A notarized affidavit with the date of publication must be submitted with the tear sheet if the date is not shown.

Day 10	OHFA receives reviews and approves the NOI/RROF and support documents.  OHFA prepares the RROF and Certification (HUD Form 7015.15) (Attachment S).

Day 11	OHFA faxes the RROF Certification (HUD Form 7015.15) (Attachment S) with the NOI/RROF documents to HUD.  OHFA will not fax the RROF to HUD before Day 11.  OHFA will mail the originals to HUD.

Day 12	First day of HUD fifteen (15) day objection period.

Day 26	Last day of HUD fifteen (15) day objection period.

Day 27	HUD forwards all objections to the RROF to OHFA and will approve or disapprove the NOI/RROF after objections are managed by OHFA.  OHFA must consider the comments and make modifications, if appropriate, in response to the comments, before it completes its environmental certification and before the recipient submits its RROF.  If approved, HUD will issue the Authority to Use Grant Funds (HUD 7015.16) (Attachment U) and notify the Grantee and OHFA.  The Grantee may begin expending project funds.   If disapproved, HUD will notify OHFA about the deficiencies.